## Slide 1: ECHO ISPCTN Junior Pilot Orientation
October 2021

## Slide 2: Topics for today
General guidelines
Timelines
Budgets
Engagement going forward?

## Slide 3: General Guidelines
Pilots need to be at least two institutions
All pilots need to be streamlined (budget, other concerns)
DCOC for:
  Central IRB
  Contracts
  Informatics
  Statistics

## Slide 4: Common themes from ECP review
Need validated outcome measures
  What measures demonstrate
STREAMLINE
  Every pilot had several comments stating it was too complex for a pilot
  Concerns about fitting budget & timeline
Site selection
  Sites included in the pilots may not be the best sites for actual implementation

## Slide 5: Junior Pilot Timelines
2022
2023
2024
2025
Period B:
Trials launch September 2022; End by August 2024
Period A:
Protocol development; PRC; DSMB; IRB
Period C:
Closeout & publications

## Slide 6
Protocol Development
PRC
DSMB
Implementation
Target: Launch September 2022
IRB approval & site addition (4-6 weeks)
Contracting (6 weeks)
Site training
Finalize CRFs, MOP, study materials
Target: PRC recommendations approved by Program Office by late March 2022
On-going CRF, data infrastructure development
Budget development
Human subjects protections planning
PRC revisions may be needed in April/May
Target: DSMB recommendations approved by Program Office by May 2022
On-going CRF development
Site selection
Budget development
If PRC revisions are required, DSMB review will be delayed until June – July
Target: Ready for PRC submission by February 2022
Statistics consultation available
Weekly meeting with NIH project scientist

## Slide 7: Timeline & Budget
October 1, 2021 – August 31, 2022 (Period A) | Jr. investigators develop protocol, and obtain approvals from the Protocol Review Committee (PRC), and Data Safety and Monitoring Board (DSMB), if proposed study involves humans may request up to a total of 30% FTE salary support for Principal Investigators (PIs) and no less than 15% FTE for a single PI maximum of 2 Multiple PIs (MPIs) from different awardee institutions is allowed per application
September 1 2022 – August 31, 2024 (Period B) | Jr. investigators implement the protocol (enrollment and follow-up of participants), complete closeout functions, and generate manuscript(s) for publication -$300K TOTAL (direct & indirect for two years) Must include Up to 30% FTE per year and no less than 15% FTE per year salary support for PI(s). A maximum of 2 MPIs from different awardee institutions is permitted per application No salary support for Sr Fac Dev DCOC support does NOT need to be included in budget

## Slide 8: Sample for Budget Assumptions
$300,000 total costs for Period B
Assuming 63% indirect rate:
  $300,000 total -> $184,000 direct + $116,000 indirect
  $184,000 direct = $92,000 / year
    PI allocation of 15% FTE per year (max $30,000/year)
    Leaves $62,000 / year for the trial